MIRA VISTA

PREFAB STEEL FRAMING QUOTE

| PROJECT | QUOTE INFORMATION |
| --- | --- |
| Location | 500 South 1040 East, American Fork, Utah |
| Owner | Four Amigos Development, LLC |
| Building | 44,400 square feet • 3 floors |
| Conversion | Wood framing converted to engineered prefab steel panels |
| Estimator | Ericson Tua’one |
| Contact | info@berwilson.com • 385-436-5507 |
| Quote date | September 16, 2026 |

BUILD FASTER WITH PREFAB STEEL The framing arrives as coordinated, labeled prefab steel panels. If Ber Wilson installs the system, the anticipated panel-installation duration is 4–6 weeks versus approximately four months for standard wood framing.

BER WILSON TURNKEY QUOTE $2,131,200 — includes engineering conversion, MEP channeling, all defined prefab framing materials, insulation within the panels, builder’s risk, and Ber Wilson installation at $15.00 per square foot, including framing equipment and crane.

# Quote Price

| Scope | Area | Rate | Amount |
| --- | --- | --- | --- |
| Engineering conversion and complete prefab panel material package | 44,400 SF | $33.00/SF | $1,465,200 |
| Ber Wilson installation, equipment, and crane | 44,400 SF | $15.00/SF | $666,000 |
| TOTAL TURNKEY QUOTE | 44,400 SF | $48.00/SF | $2,131,200 |

# Included in Turnkey Quote

Engineering conversion of the existing wood-framed plans into an engineered cold-formed steel prefab panel system.

Panel engineering, framing layouts, fabrication drawings, connection details, and coordinated panel schedules.

MEP engineering and channeling integrated into the panels, including service chases, pathways, prepunched holes, sleeves, openings, inserts, and penetrations for MEP routing.

Concrete-to-steel coordination for embeds, anchors, hold-downs, bearing points, and panel connections.

Complete defined prefab steel framing material package for approved wall, floor, and roof panels, including tracks, clips, bridging, blocking, bracing, fasteners, and required accessories.

Insulation furnished and installed within the prefab panel assemblies according to the approved panel schedule.

Simpson Strong-Tie branded hold-downs, straps, anchors, fasteners, and structural connectors included in the approved framing scope.

Builder’s risk included.

Ber Wilson field installation at $15.00 per square foot, including framing-specific lifts, telehandlers, rigging, material handling, crane, operator, panel hoisting, assembly, bracing, fastening, and erection.

PANEL DELIVERY Wall, floor, and roof framing will be fabricated and delivered as labeled, sequenced panels or panelized assemblies according to the approved fabrication package.

# Schedule Comparison

| Measure | Ber Wilson prefab installation | Standard wood framing |
| --- | --- | --- |
| Field framing duration | 4–6 weeks anticipated | Approximately 4 months |
| Projected advantage | Approximately 2.5–3 months faster | Baseline |
| MEP field time | 40%–50% projected reduction | Field layout/cutting baseline |
| Site work | Panel setting and connections | Field measuring, cutting, and assembly |

SCHEDULE BASIS The 4–6 week timeframe applies when Ber Wilson performs installation and assumes approved drawings, timely material release, complete concrete work, clear crane access, sequenced deliveries, timely inspections, and uninterrupted work areas.

# Delivery Options

The prices below separate the turnkey Ber Wilson installation from the Owner-installed option. Materials with crew training are to be quoted after Ber Wilson reviews the Owner’s crew, equipment plan, schedule, supervision needs, and requested field support.

| Option | Scope | Price |
| --- | --- | --- |
| A — Ber Wilson turnkey installation | Engineering conversion, complete prefab panel materials, builder’s risk, equipment, crane, and Ber Wilson installation. | $2,131,200 |
| B — Materials + Owner-crew training | Engineering conversion, complete prefab panel materials, training, installation planning, and agreed field support so the Owner’s crew can install. | TBQ |
| C — Separate Ber Wilson installation | Installation requested separately from the material/training package; equipment and schedule confirmed at quote. | $15.00/SF, subject to final scope |
| D — Wood-frame alternate | Separate wood-framing quotation for comparison. | TBQ |

OWNER-CREW INSTALLATION — TBQ The materials-and-training option is not priced in this quote. Ber Wilson will issue a separate TBQ proposal identifying the material package, training days, trainer count, on-site technical supervision, travel, crane/equipment responsibility, crew qualifications, installation schedule, and quality-control responsibilities.

BER WILSON INSTALLATION If Ber Wilson installs, the rate is $15.00 per square foot, totaling $666,000 for 44,400 square feet. The price includes framing installation equipment and crane, with an anticipated 4–6 week prefab steel panel-installation timeframe.

# Exclusions

MEP equipment, fixtures, ductwork, piping, conduit, wiring, controls, rough-in, installation, testing, balancing, and commissioning. MEP engineering and panel channeling are included; MEP construction is excluded.

Concrete materials, reinforcement, formwork, placement, finishing, foundations, slabs, walls, and concrete labor. Concrete interface coordination is included.

Exterior cladding and finishes, including siding, masonry veneer, stucco, exterior metal panels, rainscreen, trim, flashings, and coatings.

Drywall, gypsum board, taping, mudding, sanding, texture, painting, and interior finishes. These may be quoted separately.

Roofing, waterproofing, weather-resistive barriers, glazing, windows, doors, storefront, sealants, and firestopping unless specifically listed.

Sitework, demolition, excavation, utilities, paving, landscaping, stairs, rails, canopies, finish carpentry, and structural steel outside the prefab package.

Insulation outside the prefab panels, permits, fees, taxes, bonds, testing, special inspections, project-wide temporary services, extraordinary crane access, and abnormal site conditions.

# Payment Terms

PREFAB MATERIALS 100% of the prefab material amount is due upon receipt of invoice and before fabrication or material release. Fabrication begins after cleared funds and approved production documents.

| Ber Wilson installation milestone | Percent | Amount |
| --- | --- | --- |
| Contract execution / mobilization | 50% | $333,000 |
| 50% framing completion | 25% | $166,500 |
| 90% framing completion | 20% | $133,200 |
| Successful completion and framing inspection | 5% | $33,300 |
| TOTAL INSTALLATION | 100% | $666,000 |

The materials-and-training option will have separate payment terms in the TBQ proposal.

# Quote Terms

Quote valid for 30 calendar days and subject to final plans, approved engineering conversion, final takeoff, schedule, site review, and executed agreement.

Changes, concealed conditions, incomplete concrete, inaccurate anchors, restricted access, abnormal weather, overtime, trade interference, or remobilization may adjust price and schedule.

Fabrication begins after required approvals, production documents, and material payment are received.

Materials with Owner-crew training, drywall, cladding, MEP construction, concrete construction, and wood framing require separate written quotes.

# Acceptance

TOTAL BER WILSON TURNKEY QUOTE $2,131,200

| CLIENT ACCEPTANCE | BER WILSON |
| --- | --- |
| Company: Four Amigos Development, LLC | Estimator: Ericson Tua’one |
| Name: ______________________________ | Email: info@berwilson.com |
| Title: _______________________________ | Phone: 385-436-5507 |
| Signature: ___________________________ | Signature: ___________________________ |
| Date: _______________________________ | Date: _______________________________ |

Requested option:  ☐ Ber Wilson turnkey installation   ☐ Materials + crew training (TBQ)   ☐ Wood-frame alternate (TBQ)